## DSx
|  | Requirements |  |  |  | Delivery / Drop
|  | Development |  |  |  | GA (Beta) |  | Architecture: https://ibm.ent.box.com/file/223054933335 |  |  |  |  | Sprint 1 |  |  |  | Sprint 2 |  |  |  | Sprint 3 |  |  | Sprint 4 |  |  |  | Sprint 5 |  | Sprint 6 |  |  | Sprint 7 |  |  | Sprint 8 |  | Sprint 9
|  | Testing |  |  |  | GA, but possibly at risk |  | General: https://ibm.ent.box.com/file/223211035927 |  |  |  |  | Wk 1 |  | Wk 2 |  | Wk 1 |  | Wk 2 |  | Wk 1 |  | Wk 2 | Wk 1 |  | Wk 2 |  | Wk 1 | Wk 2 | Wk 1 |  | Wk 2 | Wk 1 |  | Wk 2 | Wk 1 | Wk 2 | Wk 1 | Wk 2
Who | Category | Epic | Github Dev | Github Design | GITHUB | Explanation | Comments | Documentation | Critical | Owner | Size | ! | 2017-09-17 |  | 2017-09-24 |  | 2017-10-01 |  | 2017-10-08 |  | 2017-10-15 |  | 2017-10-22 | 2017-10-29 |  | 2017-11-05 |  | 2017-11-12 | 2017-11-19 | 2017-11-26 |  | 2017-12-03 | 2017-12-10 |  | 2017-12-17 | 2017-12-24 | 2017-12-31 | 2018-01-07 | 2018-01-14
|  | Rstudio Integration |  | 183 | [5 empty] | Design |  |  |  | Ready
| Design | Local Community Page |  | 196 | [5 empty] | Design |  |  |  | Ready
|  | Publish Models |  | 178 | [5 empty] | Design |  |  |  | Ready
|  | Deploy Model |  | 197 | [5 empty] | Design |  |  |  | Ready
|  | Model Details Pre-Publication |  | 198 | [5 empty] | Design |  |  |  | Ready
|  | Model & Deployment List Views |  | 130 | [5 empty] | Design |  |  |  | Ready
|  | Evaluate Health |  | 135 | [5 empty] | Design |  |  |  | Ready
|  | Published Assets -> Users not logged into DSX |  | 216 | [5 empty] | Design |  |  |  | Ready
|  | DSX Local Landing Page |  | 195 | [5 empty] | Design |  |  |  | Ready
|  | Admin Alerts |  | 222 | [5 empty] | Design |  |  |  | Ready
|  | Create Notebook - Form Update |  | 212 | [5 empty] | Design |  |  |  | Ready
|  | Delete Project |  | 220 | [5 empty] | Design |  |  |  | Ready
|  | Admin - Alert Email + New User |  | 223 | [5 empty] | Design |  |  |  | Ready
|  | Un-publish Model |  | 208 | [5 empty] | Design
|  | Dataset Preview |  | 225 | [5 empty] | Design
|  | Published Assets |  | 221 | [5 empty] | Design
|  | Asset Version |  | 236 | [5 empty] | Design
|  | Browse Assets within project |  | 123 | [5 empty] | Design
IBM | Enhanced Projects | Tab navigation |  | 205 | https://github.ibm.com/PrivateCloud/dsx-core | Enhanced navigation user experience in a DSx Project. Horizontal tabs for each category(Notebooks, Runtimes, Rstudio, Datasets and etc.) |  | https://ibm.box.com/s/e6iyng2fvwngf8wsc26m3wppewjaz01q |  | Debbani | S |  |  |  | Delivery |  |  |  | Backlog? |  |  |  |  | GA
|  | Hierarchy view - multi-project Tree view (View only) | GH 258 | 295 | https://github.ibm.com/PrivateCloud/dsx-core | Allows users to view the physical location (location on file system) of assets. Possibly, ability to preview assets directly in DSx UI. | Directory tree; critical that it is customizable |  |  | Debbani | L | ! | [7 empty] | Delivery |  |  |  | GA
|  | Reference-only projects or Library projects (non-git clone) | 287 |  | https://github.ibm.com/PrivateCloud/dsx-core | Ability to refrence large datasets in multiple projects. Avoids duplication and enables governance of large datasets | This is another facet of project visibility -- not same as project in Local Community | https://ibm.ent.box.com/file/233191831446 |  | Debbani | M | [7 empty] | On Hold |  |  |  |  | Delivery
|  | Notifications |  |  | https://github.ibm.com/PrivateCloud/dsx-core
|  | Collaboration - resolve Merge Conflicts: Github-linked project | 288 | 176 | https://github.ibm.com/PrivateCloud/dsx-core | Mechanism to address merge conflicts for DSx projects linked to Github. | Important scenario ; View + merge. ; Notify users (highlighting uncommitted changes, conflicts, etc) ; Don't want DSx to become GitHub, but need basic features for when there's no GH Enterprise | https://ibm.ent.box.com/file/235769647086 |  | Debbani | L | [7 empty] | On Hold | [6 empty] | Delivery
|  | Collaboration - resolve Merge Conflicts: Local Master remote - Full support (all 4 options) | 289 |  | https://github.ibm.com/PrivateCloud/dsx-core | Merge conflicts may arise when users edit same file and push to remote "master" repository. Four different mechanisms to resolve merge conflicts. 1. Overwriting local copy with changes from master, 2. Retaining local user copy 3. Launch command line terminal and allow user to resolve conflicts using CLI tools(git, vimdiff) 4. Exporting project to filesystem to resolve conflicts in more convenient environment using user's favorite tools |  | https://ibm.ent.box.com/file/235769647086 |  | Debbani | L | [7 empty] | Backlog | [12 empty] | Delivery |  | GA
|  | Terminal in browser: Open console for any RE | 290 |  | https://github.ibm.com/PrivateCloud/dsx-core | Enable command line access to any runtime environment(Jupyter, Zeppelin, Rstudio) from DSX |  | https://ibm.ent.box.com/file/235769647086 |  | Debbani | L | [7 empty] | On Hold | [6 empty] | Delivery
|  | Terminal in browser: Open console to resolve merge conflicts | 291 |  | https://github.ibm.com/PrivateCloud/dsx-core | Enable users to resolve merge conflicts using an embedded terminal in DSx UI |  | https://ibm.ent.box.com/file/235769647086 |  | Debbani | L | [7 empty] | On Hold | [6 empty] | Delivery
|  | Deletion of Assets (notebooks, local datasets) | GH 269 |  | https://github.ibm.com/PrivateCloud/dsx-core | Deletion of notebooks and datasets from DSx web app |  |  |  | Debbani | S | [6 empty] | Delivery | [5 empty] | GA
|  | Deletion of Assets ( reference to remote datasets) | GH 269 |  | https://github.ibm.com/PrivateCloud/dsx-core | Deletion of metadata files containing information about remote datasets |  |  |  | Debbani | S | [5 empty] | Delivery | [6 empty] | GA
|  | Deletion of Assets ( reference to remote datasources) | GH 269 |  |  | Deletion of metadata files containing information about remote data sources |  |  |  | Svetlana | S | [5 empty] | Delivery |  | Completed? |  |  |  |  | GA
|  | Copy, move, rename - of assets |  |  | https://github.ibm.com/PrivateCloud/dsx-core | Copying, moving, renmaing of notebooks and datasets from DSx web app |  |  |  | Debbani | L? | [7 empty] | Backlog | [10 empty] | Delivery |  |  |  | GA
|  | Search bar across all pages -- Grids - sortable, filterable (text search) |  |  | https://github.ibm.com/PrivateCloud/dsx-core | Search bar to look quickly for projects, assets, collaborators |  |  |  | Debbani | L? | [7 empty] | Backlog | [11 empty] | Delivery |  |  | GA
|  | ______Design: Add Filtering + search mechanisms for DSXL Contents |  | 94 | [5 empty] | Design
|  | Rename Project | 292 |  | https://github.ibm.com/PrivateCloud/dsx-core | Allows users to rename projects in DSx |  |  |  | Debbani | S | ! |  |  | Delivery | [8 empty] | GA
|  | Github - Support for multiple tokens | GH 270 |  | https://github.ibm.com/PrivateCloud/dsx-core | Enables users to link both Github and Github Enterprise to DSx via access tokens. Users can create a project from Github or GHE by choosing a token from a list of previously saved tokens. |  |  |  | Debbani | M | [5 empty] | Delivery | [6 empty] | GA
|  | Collaboration - Display Merge Differences - Preview/UI |  |  | https://github.ibm.com/PrivateCloud/dsx-core | Allows users to visually examine differences in two versions of the same file | Same as GitHub Enterprise |  |  | Debbani | M | [7 empty] | Backlog | [8 empty] | Delivery
|  | Mark item in project as "Favorite" | GH 255 | [6 empty] | Bhoomaiah | ? | [7 empty] | Backlog | Bhoomaiah???
|  | Preview --->>> Only CSV files and … |  |  | https://github.ibm.com/PrivateCloud/dsx-core |  |  |  |  | Debbani
IBM | Collaboration | views: "Shared with me" & "Shared From my project with Others" |  |  | https://github.ibm.com/PrivateCloud/dsx-core | UI components allowing users to view content shared with them and content that they are sharing. | Hierarchical view might help. ; Notebook > this has been shared (e.g. box) (Git tag of the project -- can publish v1 and continue to work on v2; can have a diff/reflog of the changes) ; Look at RStudio, RShiny apps. ; Tracking lineage is very important for governance (explainability) | https://github.ibm.com/PrivateCloud/planning/issues/201 |  | Debbani | M | [14 empty] | Delivery
|  | "Share with others" as static URLs - Notebook-as-html, Notebook-as-pdf, Jupyter-as-ppt |  |  | https://github.ibm.com/PrivateCloud/dsx-core | Sharing static outputs through a static URL. | Jupyter as PowerPoint exists… |  |  | Debbani | M | [14 empty] | Delivery
|  | Views "Shared with me, others, etc." UI |  |  | https://github.ibm.com/PrivateCloud/dsx-core | UI components allowing users to view content shared with them or others. |  |  |  | Debbani | M | [7 empty] | Backlog | [6 empty] | Delivery | [7 empty] | GA
|  | "Share with others" as dynamic URLs - Rshiny App" |  |  | https://github.ibm.com/PrivateCloud/dsx-core | Ability to run Rshinny apps and share URL to running app | Dynamic application "Execute as me" -- user1 creates and publishes an app with user2, then it shows as if user2 executes. Tracks user2 as having viewed the data even if user2 may not have direct access to the data. ; User2 can run on different runtime also (might take less time than user1, depending on runtime resources). |  |  | Debbani | XL? | [7 empty] | Backlog | [12 empty] | Delivery |  | GA
|  | "Share with others" as dynamic URLs - execute Python scripts - and share output directory |  |  | https://github.ibm.com/PrivateCloud/dsx-core | Ability to execute Python scripts and share the output via a URL. |  |  |  | Debbani | XL? | [7 empty] | Backlog | [12 empty] | Delivery |  | GA
|  | "Share with others" as dynamic URLs - execute R scripts - and share output directory |  |  | https://github.ibm.com/PrivateCloud/dsx-core | Ability to execute R scripts and share the output via a URL. |  |  |  | Debbani | XL? | [7 empty] | Backlog | [12 empty] | Delivery |  | GA
|  | ______Design: Dynamic Publishing (interactive asset) |  | 203 | [5 empty] | Design
|  | Zeppelin Community Notebooks | [7 empty] | ? | ?
HDP | HDP: Hadoop Data Sources | Users can define HDFS data sources |  |  |  | Provide ability to add HDP as a data source |  |  |  | Svetlana Lucht | M |  |  | Delivery | [9 empty] | GA
|  | ______Design: HDP/ HDFS Data Sources |  | 242 | [5 empty] | Design
|  | Users can define Hive data sources |  |  |  | Provide ability to add Hive as a data source |  |  |  | Svetlana Lucht | M | [10 empty] | Delivery |  | GA
|  | Users can define BigSQL data sources |  |  |  | Provide ability to add BigSQL as a data source |  |  |  | Svetlana Lucht | M
|  | Users can define WebHDFS data sources |  |  |  | Provide ability to add WebHDFS as a data source |  |  |  | Piotr | L | [15 empty] | Delivery | [6 empty] | GA
|  | Users can define datasets pointing to HDFS files | [7 empty] | Svetlana Lucht | M |  |  | Delivery | [9 empty] | GA
|  | Users can define datasets pointing to SQL Tables | [7 empty] | Svetlana Lucht | M | [10 empty] | Delivery |  | GA
HDP | HDP: Browse & Preview HDP Datasets | HDFS / Users - in the Data Sources page & data assets panel, browse the list of HDFS files and choose to create data assets | GH 271 |  |  | Ability to browse HDFS through DSx UI | Show me all the DB2 tables, so I can create a data set for it. ; For future, think about features (columns essentially -- feature engineering), lineage, catalog | https://github.ibm.com/PrivateCloud/planning/issues/192 |  | Svetlana Lucht | XL |  |  | User story: 150 | [8 empty] | Delivery | GA
|  | ______Design: Brownse/Preview data sets |  | 243
|  | HDFS / In Insert to code panel, for any data source - browse the list of HDFS files and selects to insert code into notebook | GH 271 |  |  | Ability to preview contents of HDFS through DSx UI |  |  |  | Svetlana Lucht | L? | [12 empty] | Delivery
|  | HDFS / Select a data asset and preview (sampling) contents - for csv files, remote HDFS files | GH 271 |  |  | Ability to preview contents of HDFS through DSx UI | Sample the table to see what the data looks like. |  |  | Svetlana Lucht | M |  |  | User story: 181 |  |  |  |  | Delivery |  |  |  |  | GA
|  | SQL / Users - in the Data Sources page & data assets panel, browse the list of SQL tables and choose to create data assets |  |  |  | Ability to browse contents of a table (Hive, Hbase, BigSQL tables) through DSx UI |  |  |  | Svetlana Lucht | M | [11 empty] | Delivery | GA
|  | SQL / In Insert to code panel, for any data source - browse the list of SQL tables and selects to insert code into notebook |  |  |  | Ability to browse contents of a table (Hive, Hbase, BigSQL tables) through DSx UI |  |  |  | Svetlana Lucht | M | [11 empty] | Delivery | GA
|  | SQL / Select a data asset and preview (sample) contents - for SQL tables etc. |  |  |  | Ability to preview contents of a table (Hive, Hbase, BigSQL tables) through DSx UI |  |  |  | Svetlana Lucht | M | [11 empty] | Delivery | GA
HDP | HDP: External End-points (Spark-Livy) | Enable users to identify end-points in general (similar to data sources) with credentials/access keys. Main use case is for Spark-Livy. |  | GH 244 |  | Users will have the ability to define the remote engine endpoints (Livy). Once defined users can reference these endpoints from within their notebooks and Rstudio to execute jobs on the remote endpoint. |  |  |  | Kanchana | M | [12 empty] | GA
|  | Users should be able to refer to Spark-Livy end-points programmatically in notebooks or in R scripts. |  |  |  | Users will have the ability to define the remote engine endpoints (Livy). Once defined users can reference these endpoints from within their notebooks and Rstudio to execute jobs on the remote endpoint. |  |  |  | Kanchana | M | [12 empty] | GA
|  | Users should be able to refer to Spark-Livy end-points in DSx-ml - while training in visual model builder, deployments |  |  |  | Users will have the ability to define the remote engine endpoints (Livy). Once defined users can reference these endpoints from within their notebooks and Rstudio to execute jobs on the remote endpoint. |  |  |  | Kanchana | M | [12 empty] | GA
HDP | Security | Knox and Kerberos Support for secure HDP cluster |  |  |  | Establish trust between DSx and Hadoop cluster |  |  |  | Svetlana Lucht | L? |  |  | Delivery
|  | GDPR Compliance | GH 245 | [6 empty] | ? | [8 empty] | Backlog
|  | HIPPA Compliance | [7 empty] | ? | [8 empty] | Backlog
IBM | ML/Model Lifecycle | Push to and score on Cloud (kebab option in addition to "Deploy") | GH 253 |  |  | Ability to create a model in DSX Local and push/score on DSX Cloud | Hybrid use case. (JPMC 5-year transition-to-cloud plan -- Contact: JFP and John Thomas) |  |  | Bhoomaiah | S |  |  |  | Delivery | [8 empty] | GA
|  | Import models into Project/Assets |  |  |  | Import different models like PMML into DSX Local | Models that have been trained, and they can be different models from different frameworks (Decision Optimization, scikit-learn, etc). |  |  | Bhoomaiah | S | [7 empty] | Delivery |  |  |  |  | GA
|  | ______Design: Import Models |  | 187
|  | Work with different types of models - Spark, scikit-learn, xgboost, PMML, (Basil) |  |  |  | Ability to define different type of models |  |  |  | Bhoomaiah | L | [9 empty] | Delivery |  |  | GA
|  | Train models in DSx project context (Visual model builder, notebooks, scripts) |  |  |  | Ability to train different type of models in the project | We have visual model builder (wizard-style and Flows/Canvas, notebooks and scripts), later Decision Optimization. |  |  | Bhoomaiah | M | [9 empty] | Delivery |  |  | GA
|  | Test/Score & validate model asset in projects |  |  |  | Ability to test different type of models in the project |  |  |  | Bhoomaiah | M | [9 empty] | Delivery |  |  | GA
|  | ML with Remote Spark |  |  |  | Doing ML using customer provided Spark |  |  |  | Bhoomaiah | M | [9 empty] | Delivery
|  | Deletion of Models | [7 empty] | Bhoomaiah | [8 empty] | Delivery |  |  |  |  | GA
|  | ML in Zeppelin | GH 257 |  |  | Next step is to integrate with HDP |  |  |  | Bhoomaiah | [10 empty] | Delivery |  |  | GA
IBM | Operations | Publish Model -> Deployment & initial Model Lifecycle |  |  |  |  | https://ibm.box.com/s/cgx6bd0f8zpuaj8mymxh5z6smrrr5wiv | https://ibm.box.com/s/cgx6bd0f8zpuaj8mymxh5z6smrrr5wiv |  | Bhoomaiah | M | [12 empty] | Delivery
|  | Batch scoring published models |  |  |  | Expose APIs, End-points for predictions, enabling: (i) online scoring: synchronous REST APIs for authorized apps to invoke predictions and (ii) OFFLINE scoring: - asynchronous jobs for slow scoring cases (even for a single row), for large batches, or "daemon" processes for continuous scoring of incoming streaming data. | Some models may give an answer in seconds; others in minutes. Track invocations for governance (succeed, failed, results, etc). |  |  | Bhoomaiah | L | [14 empty] | Delivery
|  | Additional APIs/dashboards to track status and health of batch jobs | [7 empty] | Bhoomaiah | M | [14 empty] | Delivery
|  | Integrate Decision Optimization as a model within DSx - Bhoomaiah's team |  |  |  |  | https://ibm.box.com/s/qbtoiaxptph6b27y505ugf47ji5nh1uv ; Decision Optimization team in France. -- Needs to be consistent | https://ibm.ent.box.com/file/223094422434 |  | Bhoomaiah + DO team in France | [7 empty] | Delivery | [5 empty] | GA
|  | Special add-on Decision Optimization as a model - DO team | [7 empty] | Amelie Hocquette | [12 empty] | Delivery | GA
|  | INSTALLATION - PreReqCheck script |  |  |  | Changing docker version, so it doesn't taint the Kernel |  |  |  | John Westrik | ? |  |  | COMPLETED | [8 empty] | Delivery
| Governance | Project Monitoring | GH 252 | [6 empty] | Bhoomaiah | [8 empty] | Backlog
|  | Image Monitoring | GH 251 |  |  | See image mgt |  |  |  | Bhoomaiah | [8 empty] | Backlog
|  | Platform Monitoring | GH 250 | [6 empty] | Bhoomaiah | [8 empty] | Backlog
|  | Runtime Monitoring | GH 249 |  |  | See runtime enhancements |  |  |  | Bhoomaiah | [8 empty] | Backlog
|  | User Monitoring | GH 248 | [6 empty] | Bhoomaiah | [8 empty] | Backlog
IBM | Runtime Environments | Self-service "provisioning" of runtime environments - using IBM provided & customer provided images |  |  |  |  | Requests cpu/memory resources (besides start/stop) |  |  | Bhoomaiah | L | [9 empty] | Delivery |  |  | GA
|  | Access runtime environments from browser |  |  | https://github.ibm.com/PrivateCloud/dsx-core | Enable command line access to any runtime environment (Jupyter, Zeppelin, Rstudio) from DSX. | Terminal ? - say a wetty interface ? ; Command line in browser (Look at Cloudera's DSW or Jupyter Labs, RStudio shell) |  |  | Bhoomaiah/Debbani | M | [9 empty] | Delivery |  |  | GA
|  | Access runtime environments from remote clients ?? |  |  | https://github.ibm.com/PrivateCloud/dsx-core | Enable command line access to any runtime environment (Jupyter, Zeppelin, Rstudio) for a non-browser. |  |  |  | Bhoomaiah/Debbani | L | [22 empty] | GA
|  | Runtime Enhancements - Jupyter | GH 272 |  |  | Capability to allow user to specifiy how many CPU and memory to be used for a particular object type |  |  |  | Bhoomaiah | [10 empty] | Delivery
|  | Runtime Enhancements - Rstudio | GH 272 |  |  | Capability to allow user to specifiy how many CPU and memory to be used for a particular object type |  |  |  | Bhoomaiah | [10 empty] | Delivery
|  | Runtime Enhancements - Zeppelin | GH 272 |  |  | Capability to allow user to specifiy how many CPU and memory to be used for a particular object type |  |  |  | Bhoomaiah | [10 empty] | Delivery
IBM | Image Mgt | Project Administrator can create updated images for any of Jupyter images | GH 260 |  |  | The project adminstrator can make changes to these images after downloading them and running them independently (say on a laptop that may have Internet connectivity). We'd expect these changes to primarily involve adding additional packages and/or libraries to be availalbe to the notebook/framework. They upload it back to the cluster and then run it. | https://ibm.box.com/s/44gx3vmtnizur4qgl6cyfkfhnrzck5zp | https://ibm.box.com/s/44gx3vmtnizur4qgl6cyfkfhnrzck5zp |  | Steve La | XL | [11 empty] | Delivery | GA
|  | ___List and infrastructure |  |  |  | List of images that they can upload |  |  |  | Steve La | M
|  | ___Upload |  |  |  | Upload ability for folks to upload |  |  |  | Steve La | S
|  | ___Admin list | [7 empty] | Steve La | S
|  | ___Admin approve/reject/download | [7 empty] | Steve La | S
|  | ___Download | [7 empty] | Steve La | S
|  | ___Run |  |  |  | Ability to run an image |  |  |  | Steve La | XS
|  | Project Administrator can create updated images for any of Rstudio images | [7 empty] | Steve La | [8 empty] | Backlog
|  | Project Administrator can create updated images for any of Zeppelin images | [7 empty] | Steve La | [8 empty] | Backlog
|  | DSX user can select image to use for each analytics asset |  |  |  | Each asset (e.g. Jupyter Notebook) can be associated with a particular Jupyter image that has the packages required for that Notebook. |  | https://ibm.ent.box.com/file/219395191693 |  | Steve La | L | [10 empty] | Delivery |  | GA
IBM |  | Docker pull of IBM provided images from DSx Local registry (default) |  |  |  |  | Support docker login with DSx bearer token; Bring in new docker images, e.g. TensorFlow runtime. Do they need a Shell/terminal or a client of some sort? ; Right now, very simple image management. Not arbitrary images. ; People who use Docker will always use the Docker CLI directly (outside of DSx). |  |  | Piotr | L | [7 empty] | Delivery |  |  |  |  | GA
Jupyter, Zeppelin, Rstudio
Spark = Out of scope
|  | Docker pull of IBM provided images from Public Registry | [7 empty] | Piotr | L | [7 empty] | Delivery |  |  |  |  | GA
|  | Build docker images using IBM Base image | [7 empty] | Piotr | L | [7 empty] | Delivery |  |  |  |  | GA
|  | Docker push of IBM image to DSx Local registry | [7 empty] | Piotr | L | [7 empty] | Delivery |  |  |  |  | GA
IBM |  | DSx non-Admin User - View all available images usable for Runtime environments |  |  |  |  | https://ibm.box.com/s/44gx3vmtnizur4qgl6cyfkfhnrzck5zp |  |  | Piotr | L | [10 empty] | Delivery |  | GA
|  | DSx non-Admin User - View private images (not yet approved for sharing by DSx Admin) | [7 empty] | Piotr | L | [10 empty] | Delivery |  | GA
|  | DSx Admin User - Sees all images, including those docker push-ed or private images needing approval | [7 empty] | Piotr | L | [10 empty] | Delivery |  | GA
|  | DSx Admin User - Enables/disables images, approves images for sharing as Runtime environments. |  |  |  |  | Fills out/Edits additional info - description/name and image location:version |  |  | Piotr | L | [10 empty] | Delivery |  | GA
|  | Save running Runtime Environment as a Docker image (Approval needed by DSx-Admin for sharing) | 37 |  |  | General epic for all 3 images |  |  |  | Steve La | L | [22 empty] | GA
|  | Build & Automation: Dockerize & Jenkinize automation test | GH 261 | [6 empty] | Steve La | ? | [8 empty] | Delivery
|  | Create build infrastructure to custom build certain components for DSX | GH 224 | [6 empty] | Kanchana
IBM | ML/DL // Bringing in Additional Frameworks | H20 flows | GH 254 | [6 empty] | Bhoomaiah | M | [7 empty] | Delivery |  |  |  |  | GA
|  | H2O.ai | [7 empty] | Bhoomaiah | [10 empty] | Delivery
|  | Anaconda Python 3.6 (not for Spark) with Scikit learn, XGBoost | [7 empty] | Bhoomaiah |  |  | ? |  |  | GA |  |  | Backlog
|  | Caffe | [7 empty] | Bhoomaiah |  |  | ? |  |  | GA |  |  | Backlog
|  | Tensorflow | [7 empty] | Bhoomaiah |  |  | ? | [5 empty] | Backlog
IBM | Platforms | DSx on Power |  |  |  | Joint release with DSX this month, so to have a solid end-to-end machine learning & deep learning offering with hardware infrastructure optimized to run it. Its "AI in a Box. |  |  |  | John Westrik | XXL
|  | ___Validating DSX works properly on Power | GH 263 | [6 empty] | Steve La
|  | DSx on Power - upgrade to V2 (Sep) code base | [7 empty] | Indrajit Poddar | S |  | ? |  |  |  | Status? |  |  |  |  | Delivery |  | GA
|  | ___Power Broker | [7 empty] | John Westrik | ? | [7 empty] | Backlog
|  | ___Enhancements - GPU Support Power |  |  |  | Tainted Kernel Issue, change install to docker 1.12; Supported in K8S to a certain version, but need to be tested |  |  |  | John Westrik | ? | [7 empty] | Power team testing this
|  | DSx on Sailfish | [7 empty] | John Westrik | XL |  |  | GA |  |  |  |  | 1 issue left (nginx problem; Yawen looking at this)
|  | ___Deploy/score ML models on dashDB-Livy-Spark | GH 211 |  |  | Connection to Livy for remote Spark context; DSX libraries available in dashDB Spark class; validation from DSX to dashDB-Livy-Spark |  |  |  | Steve La? | ?
|  | ___Performance tests on Sailfish | GH 265 |  |  | DSX performance tests on Sailfish |  |  |  | Steve La | ?
|  | DSx on Sailfish -v2 code base | GH 259 | [6 empty] | Indrajit Poddar | L | [5 empty] | Status? | [5 empty] | Delivery
|  | DSx on Pureapp | GH 266 | [6 empty] | John Westrik | S
|  | ___Spark related functionality & file Mgt on pureAPP | GH 264 |  |  | Use all spark related functionality & filemgt on PureApp |  |  |  | Steve La | ?
|  | DSx on Linux on Z - Sept Code | [7 empty] | John Westrik | XXL |  | ? | [11 empty] | Delivery | [8 empty] | GA
|  | DSX ON X86 | [7 empty] | John Westrik
Event Store
|  | ___Event Store: Monitoring dashboard |  |  | https://github.ibm.com/PrivateCloud/eventstore-core | Open Beta was last week of Sept |  |  |  | Debbani
|  | ___Event Store: Enhancements for GA |  |  | https://github.ibm.com/PrivateCloud/eventstore-core |  |  |  |  | Debbani
|  | ___Packaged Spark & Notebook Containers for Event Store | GH 262 | [6 empty] | Steve La
|  | Upgrade Flag |  |  |  | Get to point to upgrade from release to release through flag |  |  |  | John Westrik | XL | [7 empty] | Backlog
|  | Add Ubuntu Support on PPCLE | [7 empty] | John Westrik | ? | [7 empty] | Backlog
|  | Add Ubuntu Support on x86 | [7 empty] | John Westrik | ? | [7 empty] | Backlog
|  | Firewall support on x86 | [7 empty] | John Westrik | ? | [7 empty] | Backlog
|  | Replace node storage | GH 99 | [6 empty] | John Westrik | ? | [7 empty] | Backlog
|  | Replace node master | GH 100 | [6 empty] | John Westrik | ? | [7 empty] | Backlog
|  | DSx in ICP - Developer Edition | GH 238 | [6 empty] | Kanchana |  |  | Beta | [10 empty] | GA
|  | DSx in ICP - Local Enterprise Edition | GH 237 | [6 empty] | Kanchana | L | [11 empty] | Delivery | GA
|  | DSx Developer Edition (desktop) | GH 267 |  | https://github.ibm.com/PrivateCloud/dsx-core/tree/dsxd-v1.1.1 |  |  |  |  | Debanni | L | [9 empty] | Delivery |  | Open Beta |  |  |  |  | GA
|  | Enabling DSx Trial version | GH 239 |  |  | Licensing enhancements |  | https://ibm.ent.box.com/notes/202853310327 |  | Kanchana | L | [8 empty] | Delivery |  |  |  | GA
|  | ______Design: Trial Expiration Warning |  | 210 | [5 empty] | Design
|  | Ability to publish to non-DSX user | GH 206 | [6 empty] | ?
|  | Integrate DSX with Hadoop Clusters | GH 192 | [6 empty] | Sveltana Lucht | [8 empty] | Completed?
TODAY

## Other
268 | Task
265 | User Story
264 | User Story
263 | User Story
262 | User Story | Event Store | Platforms
246 | Duplicate??
224 | To be removed
217 | Task

## Teams
John Westrik | Platforms/Install | Install Team
Steve La | Image Management | Spark Team
Svetlana Lucht | HDFS/Hive + Data Sources | HDFS Integration Team
James Spyker | License Mgt + Overall knowledge off all initiatives
Debbani |  | Desktop/Projects
Bhoomaiah |  | UI/ML/
Kanchana |  | Hortonworks integration
Piotr | Platform/Install Spark and Spark Service file transfer and key stores full admin dashboard Data Sources ( aka Connections ) as Martin mentioned image management - under development

## Sheet1 (hidden)
Sprint Plan |  | Sprint 3 |  |  |  | Sprint 4 |  |  |  | Sprint 5 |  |  | Sprint 6 |  |  | Sprint 7 |  |  |  | Sprint 8 |  |  |  | Sprint 9
|  | Wk 1 |  | Wk 2 |  | Wk 1 |  | Wk 2 |  | Wk 1 | Wk 2 |  | Wk 1 |  | Wk 2 | Wk 1 |  | Wk 2 |  | Wk 1 |  | Wk 2 |  | Wk 1 |  | Wk 2
|  | 2015-06-02 |  | 2015-06-09 |  | 2015-06-16 |  | 2015-06-23 |  | 2015-06-30 | 2015-07-07 |  | 2015-07-14 |  | 2015-07-21 | 2015-07-28 |  | 2015-08-04 |  | 2015-08-11 |  | 2015-08-18 |  | 2015-08-25 |  | 2015-09-01
Bank | Client Consent (#16 & 17) | Dev/QA | VAL
Bank | DNE Revalidation | VAL
Bank | Segmentation | VAL
Tax | CRSS Tax Event | Dev/QA | VAL
Tax | Formatted Name | [6 empty] | Req |  | Dev/QA | VAL
Bank | Bank TXN Def Update |  | Req |  | Dev/QA |  | VAL
Tax | Client Consent VW | Req | Dev/QA |  | VAL
Tax | Add Most Recent Tax Event | Req | Dev/QA |  | VAL
Tax | Add GUID to Client Consent | Dev/QA | VAL
Tax | Client Email (Historical Load) | Upload/VAL
Tax | Client DDS Tax Event | Req | Dev/QA |  | VAL
Tax | CRSS W-2 | Dev/QA |  | VAL
Tax | CRSS Name | Req |  | Dev/QA |  |  | VAL
Tax | CRSS Email | Req |  | Dev/QA |  |  | VAL
Tax | CRSS Address | Req |  | Dev/QA |  |  |  | VAL
T&B | MDM Client Insights Validation |  | Dev/QA | VAL
Tax | Segmentation | Dev/QA | VAL
Bank | Client Consent (Fraud) LT Solution | Req |  | Dev/QA |  | VAL
Bank | Bank Address Differences | Dev/QA |  | VAL
Tax | Add State Return Data to Marketing DM |  |  |  |  | Req |  |  |  | Dev/QA |  | VAL
Tax | CRSS Phone | Req | [8 empty] | Dev/QA |  |  | VAL
T&B | Connect Process Improvements | Req | [8 empty] | Dev/QA |  |  | VAL
Bank | Direct Phone | Req | [8 empty] | Dev/QA |  |  | VAL
Bank | Robodial | Req | [8 empty] | Dev/QA |  |  | VAL
Tax | Robodial | Req | [8 empty] | Dev/QA |  |  | VAL
T&B | Calling Response Data from CSO | Req | [8 empty] | Dev/QA |  |  | VAL
T&B | Get/Save Call Dispositions from Connect for C5 | Req | [8 empty] | Dev/QA |  |  | VAL
CM | Campaign 3 - Build Definitions | DBM |  |  |  | QA
CM | Campaign 3 - Suppressions | DBM |  |  |  | QA
CM | Campaign 3 - Selection Criteria | DBM |  |  |  | QA
CM | Campaign 3 - Comm Def & Export Layout |  |  | DBM |  | QA
CM | Campaign 3 - Segm, Treatm & Bus Rule Def | DBM |  |  |  | QA
CM | Campaign 3 - Response Attribution | DBM |  |  |  | QA
CM | Campaign 4 - Review Req & Build Population |  |  |  |  | DBM | QA
CM | Campaign 4 - Unidentified Data Needs |  |  |  |  | Req | Dev/QA |  | VAL
CM | Campaign 4 - Build Definitions |  |  |  |  | DBM | QA
CM | Campaign 4 - Complete Model Scoring | [5 empty] | DBM | QA
CM | Campaign 4 - Suppressions | [5 empty] | DBM | QA
CM | Campaign 4 - Selection Criteria | [5 empty] | DBM |  | QA
CM | Campaign 4 - Comm Def & Export Layout | [5 empty] | DBM |  | QA
CM | Campaign 4 - Segm, Treatm & Bus Rule Def | [7 empty] | DBM | QA
CM | Campaign 4 - Response Attribution | [7 empty] | DBM | QA
CM | Campaign 4 - Generation Campaign List | [7 empty] | DBM | QA Output
T&B | 4th of July | [8 empty] | 2015-07-04
CM | Campaign 5 - Review Req & Build Population | [9 empty] | DBM | [6 empty] | QA
CM | Campaign 5 - Unidentified Data Needs | [9 empty] | Req |  | Dev/QA |  |  |  | VAL
CM | Campaign 5 - Suppressions | [9 empty] | DBM | [6 empty] | QA
CM | Campaign 5 - Selection Criteria | [10 empty] | DBM | [5 empty] | QA
CM | Campaign 5 - Build Definitions | [10 empty] | DBM | [5 empty] | QA
CM | Campaign 5 - Comm Def & Export Layout | [11 empty] | DBM | [5 empty] | QA
CM | Campaign 5 - Complete Model Scoring | [11 empty] | DBM | [5 empty] | QA
CM | Campaign 5 - Segm, Treatm & Bus Rule Def | [11 empty] | DBM | [5 empty] | QA
CM | Campaign 5 - Response Attribution | [11 empty] | DBM | [5 empty] | QA
CM | Campaign 5 - Generation Campaign List | [12 empty] | DBM |  |  |  |  | QA Output
Bank | Embossed Card/ECPRD Changes | [9 empty] | Req |  |  |  | Dev/QA | VAL
Bank | Digital Partner ID Suppression | [11 empty] | Req |  | Dev/QA | VAL
CM | Campaign 6 - Review Req & Build Population | [18 empty] | DBM
CM | Campaign 6 - Unidentified Data Needs | [18 empty] | Req | Dev/QA |  | VAL
CM | Campaign 6 - Suppressions | [18 empty] | DBM
CM | Campaign 6 - Selection Criteria | [19 empty] | DBM
CM | Campaign 6 - Build Definitions | [19 empty] | DBM
CM | Visual Analtyics Training | [20 empty] | Training
CM | Campaign 6 - Comm Def & Export Layout | [20 empty] | DBM
CM | Campaign 6 - Complete Model Scoring | [20 empty] | DBM
CM | Campaign 6 - Segm, Treatm & Bus Rule Def | [20 empty] | DBM
CM | Campaign 6 - Response Attribution | [20 empty] | DBM
CM | Campaign 6 - Generation Campaign List | [20 empty] | DBM | QA Output
CM | Campaign 7 - Review Req & Build Population | [22 empty] | DBM
CM | Campaign 7 - Unidentified Data Needs | [22 empty] | Req | Dev/QA |  | VAL
CM | Campaign 7 - Suppressions | [22 empty] | DBM
CM | Campaign 7 - Selection Criteria | [23 empty] | DBM
CM | Campaign 7 - Build Definitions | [23 empty] | DBM
CM | Campaign 7 - Comm Def & Export Layout | [24 empty] | DBM
CM | Campaign 7 - Complete Model Scoring | [24 empty] | DBM
CM | Campaign 7 - Segm, Treatm & Bus Rule Def | [24 empty] | DBM
CM | Campaign 7 - Response Attribution | [24 empty] | DBM
CM | Campaign 7 - Generation Campaign List | [24 empty] | DBM | QA Output
Tax | Add Office & Tax Pro Info to Appointment VW | [13 empty] | Req | Dev/QA |  | VAL
Tax | Acquisition Clients | [13 empty] | Req | Dev/QA | VAL
Tax | Load Historical Insights from CA | [14 empty] | Req |  |  |  | Dev/QA |  |  | VAL
T&B | Tokenization | [15 empty] | Req |  |  |  |  | Dev/QA |  |  | VAL
Tax | Load File of Deceased Clients into Client DDS | [18 empty] | Req |  |  |  | Dev/QA |  | VAL
Tax | Add Tax Form Data to Marketing DM | [20 empty] | Req |  |  |  | Dev/QA
Tax | Add Tax Form LKP Info to Marketing DM
Tax | Add 1040 Tax Info to Marketing DM
Tax | Add Tax Discount Data to Marketing DM
Tax | Add Additional Product Data to Marketing DM
T&B | Obtain Prospective Client Info from KANA
Tax | Healthcare Disclose/Go Health Consent
Tax | Add Tax Dependent Data to Marketing DM
Tax | Send DM and Email Campaign Info to Connect
Tax | Accessing NPS data within CRM
Tax | Client Consent (Fraud) Blacklisted Suppression

## Products (hidden)
DSx Developer
DSx on ICP
DSx Local
DSx-HDP embedded
Ecosystem Integration

## Legend
(blank) | No planned activity
Requirements | Initial discussions
Development | Dev work in progress
Testing | QA & debugging
Beta | Scheduled Beta
GA | Scheduled GA
GA | GA Deliverable at risk